## records
id | recordType | project | projectId | projectName | projectLeadUserName | issueKey | issueId | issueCreated | issueUpdated | issueCreatorUserName | issueDueDate | issueRemainingEstimate | issueOriginalEstimate | issuePriority | issueReporter | issueStatus | issueTotalTimeSpent | issueVotes | issueWatches | issueResolution | issueResolutionDate | commentId | commentAuthor | commentAuthorKey | commentCreated | commentUpdated | commentUpdateAuthor | worklogId | worklogAuthor | worklogAuthorKey | worklogCreated | worklogStarted | worklogUpdated | worklogTimeSpent | commentText | worklogText
0 | I | APPDEV | 10200 | AppDev | alexA | APPDEV-2 | 10301 | 2019-01-19 19:37 | 2019-01-19 22:34 | admin |  | 46800 | 115200 | Medium | admin | In Progress | 68400 | 8 | 3
1 | C | APPDEV | 10200 | AppDev | alexA | APPDEV-2 | 10301 | 2019-01-19 19:37 | 2019-01-19 22:34 | admin |  | 46800 | 115200 | Medium | admin | In Progress | 68400 | 8 | 3 |  |  | 10216 | candiceC | candicec | 2019-01-19 22:13 | 2019-01-19 22:13 | candiceC | [7 empty] | The shunting yard algorithm is complete and merged to Dev.
2 | C | APPDEV | 10200 | AppDev | alexA | APPDEV-2 | 10301 | 2019-01-19 19:37 | 2019-01-19 22:34 | admin |  | 46800 | 115200 | Medium | admin | In Progress | 68400 | 8 | 3 |  |  | 10218 | davidD | davidd | 2019-01-19 22:17 | 2019-01-19 22:17 | davidD | [7 empty] | Thanks Candice, we'll get to work on upgrading the parser to leverage this!
3 | W | APPDEV | 10200 | AppDev | alexA | APPDEV-2 | 10301 | 2019-01-19 19:37 | 2019-01-19 22:34 | admin |  | 46800 | 115200 | Medium | admin | In Progress | 68400 | 8 | 3 | [8 empty] | 10223 | Brian Boswell | brianb | 2019-01-19 22:22 | 2019-01-09 17:00 | 2019-01-19 22:22 | 21600 |  | I've changed the interface to use the new algorithm.
4 | W | APPDEV | 10200 | AppDev | alexA | APPDEV-2 | 10301 | 2019-01-19 19:37 | 2019-01-19 22:34 | admin |  | 46800 | 115200 | Medium | admin | In Progress | 68400 | 8 | 3 | [8 empty] | 10228 | David Doswell | davidd | 2019-01-19 22:31 | 2019-01-11 17:00 | 2019-01-19 22:31 | 28800 |  | The parser is close to finished. The main functions have all been changed to handle the new objects.
5 | W | APPDEV | 10200 | AppDev | alexA | APPDEV-2 | 10301 | 2019-01-19 19:37 | 2019-01-19 22:34 | admin |  | 46800 | 115200 | Medium | admin | In Progress | 68400 | 8 | 3 | [8 empty] | 10229 | David Doswell | davidd | 2019-01-19 22:34 | 2019-01-14 14:00 | 2019-01-19 22:34 | 18000 |  | All done and committed to DEV.
6 | I | APPDEV | 10200 | AppDev | alexA | APPDEV-1 | 10300 | 2019-01-19 19:35 | 2019-01-19 22:21 | admin |  | 54000 | 144000 | Medium | admin | Done | 90000 | 4 | 4
7 | C | APPDEV | 10200 | AppDev | alexA | APPDEV-1 | 10300 | 2019-01-19 19:35 | 2019-01-19 22:21 | admin |  | 54000 | 144000 | Medium | admin | Done | 90000 | 4 | 4 |  |  | 10202 | alexA | alexa | 2019-01-19 20:49 | 2019-01-19 20:49 | alexA | [7 empty] | Can I use DAL v. 3.6 for this prototype of should I stick with 3.5?
8 | C | APPDEV | 10200 | AppDev | alexA | APPDEV-1 | 10300 | 2019-01-19 19:35 | 2019-01-19 22:21 | admin |  | 54000 | 144000 | Medium | admin | Done | 90000 | 4 | 4 |  |  | 10203 | brianB | brianb | 2019-01-19 20:50 | 2019-01-19 20:50 | brianB | [7 empty] | DAL v. 3.6 is almost through testing. We should definitely use it.
9 | C | APPDEV | 10200 | AppDev | alexA | APPDEV-1 | 10300 | 2019-01-19 19:35 | 2019-01-19 22:21 | admin |  | 54000 | 144000 | Medium | admin | Done | 90000 | 4 | 4 |  |  | 10206 | candiceC | candicec | 2019-01-19 21:26 | 2019-01-19 21:26 | candiceC | [7 empty] | I've rebuilt the test cases to use Euler angles.
10 | W | APPDEV | 10200 | AppDev | alexA | APPDEV-1 | 10300 | 2019-01-19 19:35 | 2019-01-19 22:21 | admin |  | 54000 | 144000 | Medium | admin | Done | 90000 | 4 | 4 | [8 empty] | 10211 | Candice Chapman | candicec | 2019-01-19 21:37 | 2019-01-05 17:00 | 2019-01-19 21:37 | 7200 |  | All testing is complete. All cases passed!
11 | W | APPDEV | 10200 | AppDev | alexA | APPDEV-1 | 10300 | 2019-01-19 19:35 | 2019-01-19 22:21 | admin |  | 54000 | 144000 | Medium | admin | Done | 90000 | 4 | 4 | [8 empty] | 10217 | Alex Alexander | alexa | 2019-01-19 22:11 | 2019-01-07 17:00 | 2019-01-19 22:11 | 28800 |  | Implemented the data layer.
12 | W | APPDEV | 10200 | AppDev | alexA | APPDEV-1 | 10300 | 2019-01-19 19:35 | 2019-01-19 22:21 | admin |  | 54000 | 144000 | Medium | admin | Done | 90000 | 4 | 4 | [8 empty] | 10219 | Alex Alexander | alexa | 2019-01-19 22:14 | 2019-01-08 17:00 | 2019-01-19 22:14 | 28800 |  | Building the interface.
13 | W | APPDEV | 10200 | AppDev | alexA | APPDEV-1 | 10300 | 2019-01-19 19:35 | 2019-01-19 22:21 | admin |  | 54000 | 144000 | Medium | admin | Done | 90000 | 4 | 4 | [8 empty] | 10222 | Alex Alexander | alexa | 2019-01-19 22:21 | 2019-01-09 16:00 | 2019-01-19 22:21 | 25200 |  | The interface is finished. Mock-up art assets used. I'll replace them as soon as our art assets pass review.
14 | I | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3
15 | C | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 |  |  | 10223 | davidD | davidd | 2019-01-19 22:32 | 2019-01-19 22:32 | davidD | [7 empty] | Can we book the theatre or should we use the large conference room?
16 | C | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 |  |  | 10224 | yanniY | yanniy | 2019-01-19 22:33 | 2019-01-19 22:33 | yanniY | [7 empty] | You can use the theatre, we'll get our stuff cleared out ASAP.
17 | W | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 | [8 empty] | 10233 | David Doswell | davidd | 2019-01-19 22:43 | 2019-01-15 17:00 | 2019-01-19 22:43 | 28800 |  | Started building the presentation materials.
18 | W | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 | [8 empty] | 10236 | David Doswell | davidd | 2019-01-19 22:46 | 2019-01-16 17:00 | 2019-01-19 22:46 | 28800 |  | Almost done with the presentation. I still need to clean up the math symbols.
19 | W | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 | [8 empty] | 10240 | David Doswell | davidd | 2019-01-19 22:55 | 2019-01-17 17:00 | 2019-01-19 22:55 | 28800 |  | The presentation materials are complete. Eric, would you mind reading them over?
20 | W | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 | [8 empty] | 10242 | Eric Ericson | erice | 2019-01-19 22:58 | 2019-01-18 14:00 | 2019-01-19 22:58 | 7200 |  | These look very comprehensive. My only suggestion is based around time. Maybe you could condense some of the benefits slides and then have more time for the implementation slides?
21 | W | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 | [8 empty] | 10253 | Eric Ericson | erice | 2019-01-19 23:22 | 2019-01-22 13:00 | 2019-01-19 23:22 | 3600 |  | Everything looks very impressive. This will be a great presentation.
22 | W | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 | [8 empty] | 10254 | David Doswell | davidd | 2019-01-19 23:24 | 2019-01-22 12:00 | 2019-01-19 23:24 | 10800 |  | Good point. I suppose everyone already basically understands the benefits. I just need to breeze over the. I've finished making those adjustments.
23 | W | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 | [8 empty] | 10263 | David Doswell | davidd | 2019-01-19 23:37 | 2019-01-25 17:00 | 2019-01-19 23:37 | 10800 |  | Delivering presentation and follow-up.
24 | W | ARCH | 10201 | Architecture | davidD | ARCH-2 | 10303 | 2019-01-19 19:38 | 2019-01-19 23:53 | admin |  | 0 | 57600 | Medium | admin | In Progress | 129600 | 3 | 3 | [8 empty] | 10271 | Eric Ericson | erice | 2019-01-19 23:53 | 2019-01-31 12:00 | 2019-01-19 23:53 | 10800 |  | Reivews analysed with David. Feedback documented. Good job, David!
25 | I | ARCH | 10201 | Architecture | davidD | ARCH-1 | 10302 | 2019-01-19 19:37 | 2019-01-19 23:04 | admin |  | 0 | 10800 | Medium | admin | Done | 118800 | 3 | 3
26 | C | ARCH | 10201 | Architecture | davidD | ARCH-1 | 10302 | 2019-01-19 19:37 | 2019-01-19 23:04 | admin |  | 0 | 10800 | Medium | admin | Done | 118800 | 3 | 3 |  |  | 10221 | davidD | davidd | 2019-01-19 22:28 | 2019-01-19 22:28 | davidD | [7 empty] | Scalability is our largest concern here. We need to set up a meeting about it.
27 | C | ARCH | 10201 | Architecture | davidD | ARCH-1 | 10302 | 2019-01-19 19:37 | 2019-01-19 23:04 | admin |  | 0 | 10800 | Medium | admin | Done | 118800 | 3 | 3 |  |  | 10222 | brianB | brianb | 2019-01-19 22:30 | 2019-01-19 22:30 | brianB | [7 empty] | I've set up the meeting. The invite should be in your inbox shortly.
28 | W | ARCH | 10201 | Architecture | davidD | ARCH-1 | 10302 | 2019-01-19 19:37 | 2019-01-19 23:04 | admin |  | 0 | 10800 | Medium | admin | Done | 118800 | 3 | 3 | [8 empty] | 10226 | David Doswell | davidd | 2019-01-19 22:27 | 2019-01-10 14:00 | 2019-01-19 22:27 | 21600 |  | Review complete.
29 | W | ARCH | 10201 | Architecture | davidD | ARCH-1 | 10302 | 2019-01-19 19:37 | 2019-01-19 23:04 | admin |  | 0 | 10800 | Medium | admin | Done | 118800 | 3 | 3 | [8 empty] | 10227 | David Doswell | davidd | 2019-01-19 22:29 | 2019-01-10 17:00 | 2019-01-19 22:29 | 7200 |  | Worked on upgrading the parser.
30 | W | ARCH | 10201 | Architecture | davidD | ARCH-1 | 10302 | 2019-01-19 19:37 | 2019-01-19 23:04 | admin |  | 0 | 10800 | Medium | admin | Done | 118800 | 3 | 3 | [8 empty] | 10237 | Brian Boswell | brianb | 2019-01-19 22:48 | 2019-01-16 17:00 | 2019-01-19 22:48 | 28800 |  | Re-factoring the data design.
31 | W | ARCH | 10201 | Architecture | davidD | ARCH-1 | 10302 | 2019-01-19 19:37 | 2019-01-19 23:04 | admin |  | 0 | 10800 | Medium | admin | Done | 118800 | 3 | 3 | [8 empty] | 10241 | Brian Boswell | brianb | 2019-01-19 22:56 | 2019-01-17 17:00 | 2019-01-19 22:56 | 28800 |  | More re-factoring work today.
32 | W | ARCH | 10201 | Architecture | davidD | ARCH-1 | 10302 | 2019-01-19 19:37 | 2019-01-19 23:04 | admin |  | 0 | 10800 | Medium | admin | Done | 118800 | 3 | 3 | [8 empty] | 10244 | Brian Boswell | brianb | 2019-01-19 23:04 | 2019-01-18 18:00 | 2019-01-19 23:04 | 32400 |  | Re-factoring complete and resubmitted for architecture review.
33 | I | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3
34 | C | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3 |  |  | 10214 | gabbyG | gabbyg | 2019-01-19 21:44 | 2019-01-19 21:44 | gabbyG | [7 empty] | I've chosen the bright theme. I'll push those assets today. I'll also push a space theme as a POC.
35 | C | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3 |  |  | 10231 | gabbyG | gabbyg | 2019-01-19 23:06 | 2019-01-19 23:06 | gabbyG | [7 empty] | Could someone in WebDev send me the stylesheet for the project X website?
36 | C | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3 |  |  | 10232 | xavierX | xavierx | 2019-01-19 23:08 | 2019-01-19 23:08 | xavierX | [7 empty] | Sure Gabby, it's in the dev folder for project X > website > css > main.css
37 | W | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3 | [8 empty] | 10203 | Gabby Golf | gabbyg | 2019-01-19 21:19 | 2019-01-03 17:00 | 2019-01-19 21:19 | 28800 |  | Reviewing themes.
38 | W | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3 | [8 empty] | 10208 | Gabby Golf | gabbyg | 2019-01-19 21:29 | 2019-01-04 17:00 | 2019-01-19 21:29 | 28800 |  | Testing impact.
39 | W | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3 | [8 empty] | 10215 | Gabby Golf | gabbyg | 2019-01-19 21:43 | 2019-01-07 13:00 | 2019-01-19 21:43 | 18000 |  | Cleaning up assets and committing to DEV
40 | W | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3 | [8 empty] | 10246 | Gabby Golf | gabbyg | 2019-01-19 23:06 | 2019-01-21 10:00 | 2019-01-19 23:06 | 7200 |  | Preparing stylesheet modifications.
41 | W | ART | 10202 | Art | gabbyG | ART-3 | 10306 | 2019-01-19 19:40 | 2019-01-19 23:17 | admin |  | 0 | 28800 | Medium | admin | To Do | 97200 | 14 | 3 | [8 empty] | 10251 | Gabby Golf | gabbyg | 2019-01-19 23:17 | 2019-01-21 17:00 | 2019-01-19 23:17 | 14400 |  | Assets updated and committed to DEV
42 | I | ART | 10202 | Art | gabbyG | ART-2 | 10305 | 2019-01-19 19:39 | 2019-01-19 23:16 | admin |  | 3600 | 86400 | Medium | admin | In Progress | 82800 | 2 | 2
43 | C | ART | 10202 | Art | gabbyG | ART-2 | 10305 | 2019-01-19 19:39 | 2019-01-19 23:16 | admin |  | 3600 | 86400 | Medium | admin | In Progress | 82800 | 2 | 2 |  |  | 10235 | frankF | frankf | 2019-01-19 23:12 | 2019-01-19 23:12 | frankF | [7 empty] | The mediterranean backdrop is finished.
44 | C | ART | 10202 | Art | gabbyG | ART-2 | 10305 | 2019-01-19 19:39 | 2019-01-19 23:16 | admin |  | 3600 | 86400 | Medium | admin | In Progress | 82800 | 2 | 2 |  |  | 10236 | frankF | frankf | 2019-01-19 23:16 | 2019-01-19 23:16 | frankF | [7 empty] | I've committed it to DEV.
45 | W | ART | 10202 | Art | gabbyG | ART-2 | 10305 | 2019-01-19 19:39 | 2019-01-19 23:16 | admin |  | 3600 | 86400 | Medium | admin | In Progress | 82800 | 2 | 2 | [8 empty] | 10248 | Frank Frampton | frankf | 2019-01-19 23:12 | 2019-01-21 16:00 | 2019-01-19 23:12 | 25200 |  | Final renders.
46 | W | ART | 10202 | Art | gabbyG | ART-2 | 10305 | 2019-01-19 19:39 | 2019-01-19 23:16 | admin |  | 3600 | 86400 | Medium | admin | In Progress | 82800 | 2 | 2 | [8 empty] | 10249 | Frank Frampton | frankf | 2019-01-19 23:15 | 2019-01-17 17:00 | 2019-01-19 23:15 | 28800 |  | Gathering art assets
47 | W | ART | 10202 | Art | gabbyG | ART-2 | 10305 | 2019-01-19 19:39 | 2019-01-19 23:16 | admin |  | 3600 | 86400 | Medium | admin | In Progress | 82800 | 2 | 2 | [8 empty] | 10250 | Frank Frampton | frankf | 2019-01-19 23:16 | 2019-01-18 17:00 | 2019-01-19 23:16 | 28800 |  | Touchups and replacements complete
48 | I | ART | 10202 | Art | gabbyG | ART-1 | 10304 | 2019-01-19 19:39 | 2019-01-19 19:39 | admin |  | 194400 | 194400 | Medium | admin | Done |  | 1 | 1
49 | I | DATASYS | 10204 | Data Systems | lauraL | DATASYS-2 | 10308 | 2019-01-19 19:41 | 2019-01-19 21:39 | admin |  | 90000 | 115200 | Medium | admin | In Progress | 25200 | 14 | 4
50 | C | DATASYS | 10204 | Data Systems | lauraL | DATASYS-2 | 10308 | 2019-01-19 19:41 | 2019-01-19 21:39 | admin |  | 90000 | 115200 | Medium | admin | In Progress | 25200 | 14 | 4 |  |  | 10207 | ericE | erice | 2019-01-19 21:28 | 2019-01-19 21:28 | ericE | [7 empty] | Your design is great. Would you please schedule a presentation to the developers?
51 | C | DATASYS | 10204 | Data Systems | lauraL | DATASYS-2 | 10308 | 2019-01-19 19:41 | 2019-01-19 21:39 | admin |  | 90000 | 115200 | Medium | admin | In Progress | 25200 | 14 | 4 |  |  | 10208 | lauraL | laural | 2019-01-19 21:31 | 2019-01-19 21:31 | lauraL | [7 empty] | Thanks! I've booked the design presentation in Outlook and invited all the Dev teams.
52 | C | DATASYS | 10204 | Data Systems | lauraL | DATASYS-2 | 10308 | 2019-01-19 19:41 | 2019-01-19 21:39 | admin |  | 90000 | 115200 | Medium | admin | In Progress | 25200 | 14 | 4 |  |  | 10210 | norrisN | norrisn | 2019-01-19 21:38 | 2019-01-19 21:38 | norrisN | [7 empty] | Could you add the DevOps team to the invite?
53 | C | DATASYS | 10204 | Data Systems | lauraL | DATASYS-2 | 10308 | 2019-01-19 19:41 | 2019-01-19 21:39 | admin |  | 90000 | 115200 | Medium | admin | In Progress | 25200 | 14 | 4 |  |  | 10211 | lauraL | laural | 2019-01-19 21:38 | 2019-01-19 21:38 | lauraL | [7 empty] | Done.
54 | W | DATASYS | 10204 | Data Systems | lauraL | DATASYS-2 | 10308 | 2019-01-19 19:41 | 2019-01-19 21:39 | admin |  | 90000 | 115200 | Medium | admin | In Progress | 25200 | 14 | 4 | [8 empty] | 10207 | Eric Ericson | erice | 2019-01-19 21:27 | 2019-01-04 14:00 | 2019-01-19 21:27 | 10800 |  | Design review complete.
55 | W | DATASYS | 10204 | Data Systems | lauraL | DATASYS-2 | 10308 | 2019-01-19 19:41 | 2019-01-19 21:39 | admin |  | 90000 | 115200 | Medium | admin | In Progress | 25200 | 14 | 4 | [8 empty] | 10209 | Laura Lima | laural | 2019-01-19 21:31 | 2019-01-04 17:00 | 2019-01-19 21:31 | 3600 |  | Wrapping up notes and booking resources.
56 | W | DATASYS | 10204 | Data Systems | lauraL | DATASYS-2 | 10308 | 2019-01-19 19:41 | 2019-01-19 21:39 | admin |  | 90000 | 115200 | Medium | admin | In Progress | 25200 | 14 | 4 | [8 empty] | 10212 | Laura Lima | laural | 2019-01-19 21:39 | 2019-01-07 11:00 | 2019-01-19 21:39 | 10800 |  | Highlighting points that will interest the DevOps team and extending invite.
57 | I | DATASYS | 10204 | Data Systems | lauraL | DATASYS-1 | 10307 | 2019-01-19 19:40 | 2019-01-19 22:45 | admin |  | 3600 | 57600 | Medium | admin | Done | 54000 | 3 | 3
58 | C | DATASYS | 10204 | Data Systems | lauraL | DATASYS-1 | 10307 | 2019-01-19 19:40 | 2019-01-19 22:45 | admin |  | 3600 | 57600 | Medium | admin | Done | 54000 | 3 | 3 |  |  | 10225 | henryH | henryh | 2019-01-19 22:35 | 2019-01-19 22:35 | henryH | [7 empty] | I'd like this to run overnight, but I'm concerned that there will be heavy reporting traffic just after midnight. My stuff should take about 45 minutes to run. When is the best time?
59 | C | DATASYS | 10204 | Data Systems | lauraL | DATASYS-1 | 10307 | 2019-01-19 19:40 | 2019-01-19 22:45 | admin |  | 3600 | 57600 | Medium | admin | Done | 54000 | 3 | 3 |  |  | 10227 | robertR | robertr | 2019-01-19 22:38 | 2019-01-19 22:38 | robertR | [7 empty] | Most of the reporting traffic finishes by 2:30 am. Our daily traffic minimum is between 3:45am and 5:00am. I'd think 4:00am is a good time to run your backups.
60 | W | DATASYS | 10204 | Data Systems | lauraL | DATASYS-1 | 10307 | 2019-01-19 19:40 | 2019-01-19 22:45 | admin |  | 3600 | 57600 | Medium | admin | Done | 54000 | 3 | 3 | [8 empty] | 10230 | Henry Hardrata | henryh | 2019-01-19 22:36 | 2019-01-14 17:00 | 2019-01-19 22:36 | 28800 |  | Created backup scripts.
61 | W | DATASYS | 10204 | Data Systems | lauraL | DATASYS-1 | 10307 | 2019-01-19 19:40 | 2019-01-19 22:45 | admin |  | 3600 | 57600 | Medium | admin | Done | 54000 | 3 | 3 | [8 empty] | 10231 | Henry Hardrata | henryh | 2019-01-19 22:41 | 2019-01-15 10:00 | 2019-01-19 22:41 | 3600 |  | The backups completed successfully in 39 minutes.
62 | W | DATASYS | 10204 | Data Systems | lauraL | DATASYS-1 | 10307 | 2019-01-19 19:40 | 2019-01-19 22:45 | admin |  | 3600 | 57600 | Medium | admin | Done | 54000 | 3 | 3 | [8 empty] | 10232 | Henry Hardrata | henryh | 2019-01-19 22:42 | 2019-01-15 15:00 | 2019-01-19 22:42 | 10800 |  | The restores completed successfully in 45 minutes.
63 | W | DATASYS | 10204 | Data Systems | lauraL | DATASYS-1 | 10307 | 2019-01-19 19:40 | 2019-01-19 22:45 | admin |  | 3600 | 57600 | Medium | admin | Done | 54000 | 3 | 3 | [8 empty] | 10234 | Henry Hardrata | henryh | 2019-01-19 22:45 | 2019-01-15 21:08 | 2019-01-19 22:45 | 10800 |  | Set backups to run tonight.
64 | I | DEV | 10000 | Development | admin | DEV-6 | 10005 | 2018-12-04 17:59 | 2018-12-04 17:53 | admin |  |  |  | Medium | admin | In Progress |  | 8 | 0
65 | I | DEV | 10000 | Development | admin | DEV-5 | 10004 | 2018-12-04 17:59 | 2018-12-04 17:54 | admin |  |  |  | Medium | admin | Done |  | 12 | 0
66 | I | DEV | 10000 | Development | admin | DEV-4 | 10003 | 2018-12-04 17:59 | 2018-12-04 17:55 | admin |  |  |  | Medium | admin | To Do |  | 22 | 0
67 | I | DEV | 10000 | Development | admin | DEV-3 | 10002 | 2018-12-04 17:59 | 2018-12-04 17:56 | admin |  |  | 300 | Medium | admin | Selected for Development |  | 25 | 0
68 | C | DEV | 10000 | Development | admin | DEV-3 | 10002 | 2018-12-04 17:59 | 2018-12-04 17:56 | admin |  |  | 300 | Medium | admin | Selected for Development |  | 25 | 0 |  |  | 10000 | admin | admin | 2018-12-04 17:59 | 2018-12-04 17:59 | admin | [7 empty] | Which way are you going to add your comment? * Keyboard shortcut: !m.png! * Clicking the Comment button below * Clicking the Comment button in the top section * Using the Operations Dialog keyboard shortcut: !dot.png! and then typing 'comment'
69 | I | DEV | 10000 | Development | admin | DEV-2 | 10001 | 2018-12-04 17:59 | 2018-12-04 17:57 | admin |  |  |  | Medium | admin | In Progress |  | 18 | 0
70 | I | DEV | 10000 | Development | admin | DEV-1 | 10000 | 2018-12-04 17:59 | 2019-01-09 22:56 | admin |  | 0 |  | Medium | admin | Done | 900 | 1 | 1
71 | C | DEV | 10000 | Development | admin | DEV-1 | 10000 | 2018-12-04 17:59 | 2019-01-09 22:56 | admin |  | 0 |  | Medium | admin | Done | 900 | 1 | 1 |  |  | 10100 | admin | admin | 2019-01-09 22:56 | 2019-01-09 22:56 | admin | [7 empty] | Hello World of Special Characters! Try this ~`!@#$%^&*()';:\n\r\{[}]_-+=¦?/><,\,\n\r\w%3D%27 Did it work?
72 | W | DEV | 10000 | Development | admin | DEV-1 | 10000 | 2018-12-04 17:59 | 2019-01-09 22:56 | admin |  | 0 |  | Medium | admin | Done | 900 | 1 | 1 | [8 empty] | 10000 | admin | admin | 2018-12-04 18:25 | 2018-12-04 18:24 | 2018-12-04 18:25 | 900 |  | I did something.
73 | I | DEVOPS | 10205 | DevOps | majorM | DEVOPS-2 | 10310 | 2019-01-19 19:42 | 2019-01-19 23:41 | admin |  | 0 | 28800 | Medium | admin | In Progress | 28800 | 3 | 3
74 | C | DEVOPS | 10205 | DevOps | majorM | DEVOPS-2 | 10310 | 2019-01-19 19:42 | 2019-01-19 23:41 | admin |  | 0 | 28800 | Medium | admin | In Progress | 28800 | 3 | 3 |  |  | 10242 | norrisN | norrisn | 2019-01-19 23:35 | 2019-01-19 23:35 | norrisN | [7 empty] | The scripts are written and ready to throw at the test environment as soon as product X is in place.
75 | C | DEVOPS | 10205 | DevOps | majorM | DEVOPS-2 | 10310 | 2019-01-19 19:42 | 2019-01-19 23:41 | admin |  | 0 | 28800 | Medium | admin | In Progress | 28800 | 3 | 3 |  |  | 10244 | majorM | majorm | 2019-01-19 23:41 | 2019-01-19 23:41 | majorM | [7 empty] | Thanks Norris, I'll schedule the deployment.
76 | W | DEVOPS | 10205 | DevOps | majorM | DEVOPS-2 | 10310 | 2019-01-19 19:42 | 2019-01-19 23:41 | admin |  | 0 | 28800 | Medium | admin | In Progress | 28800 | 3 | 3 | [8 empty] | 10262 | Norris November | norrisn | 2019-01-19 23:35 | 2019-01-25 15:00 | 2019-01-19 23:35 | 21600 |  | Writing new scripts.
77 | W | DEVOPS | 10205 | DevOps | majorM | DEVOPS-2 | 10310 | 2019-01-19 19:42 | 2019-01-19 23:41 | admin |  | 0 | 28800 | Medium | admin | In Progress | 28800 | 3 | 3 | [8 empty] | 10265 | Norris November | norrisn | 2019-01-19 23:38 | 2019-01-28 10:00 | 2019-01-19 23:38 | 7200 |  | Updating documentation.
78 | I | DEVOPS | 10205 | DevOps | majorM | DEVOPS-1 | 10309 | 2019-01-19 19:41 | 2019-01-19 23:30 | admin |  | 0 | 21600 | Medium | admin | Done | 32400 | 3 | 3
79 | C | DEVOPS | 10205 | DevOps | majorM | DEVOPS-1 | 10309 | 2019-01-19 19:41 | 2019-01-19 23:30 | admin |  | 0 | 21600 | Medium | admin | Done | 32400 | 3 | 3 |  |  | 10237 | majorM | majorm | 2019-01-19 23:26 | 2019-01-19 23:26 | majorM | [7 empty] | The update has cleared review. It shouldn't break anything.
80 | C | DEVOPS | 10205 | DevOps | majorM | DEVOPS-1 | 10309 | 2019-01-19 19:41 | 2019-01-19 23:30 | admin |  | 0 | 21600 | Medium | admin | Done | 32400 | 3 | 3 |  |  | 10239 | saraS | saras | 2019-01-19 23:30 | 2019-01-19 23:30 | saraS | [7 empty] | It's live in the TEST environment and I'm getting data!
81 | W | DEVOPS | 10205 | DevOps | majorM | DEVOPS-1 | 10309 | 2019-01-19 19:41 | 2019-01-19 23:30 | admin |  | 0 | 21600 | Medium | admin | Done | 32400 | 3 | 3 | [8 empty] | 10256 | Major Minor | majorm | 2019-01-19 23:26 | 2019-01-23 14:00 | 2019-01-19 23:26 | 21600 |  | Reviewing the modules in the update
82 | W | DEVOPS | 10205 | DevOps | majorM | DEVOPS-1 | 10309 | 2019-01-19 19:41 | 2019-01-19 23:30 | admin |  | 0 | 21600 | Medium | admin | Done | 32400 | 3 | 3 | [8 empty] | 10257 | Major Minor | majorm | 2019-01-19 23:27 | 2019-01-23 17:00 | 2019-01-19 23:27 | 10800 |  | Publishing to the test environment and updating documentation.
83 | I | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-3 | 10313 | 2019-01-19 19:44 | 2019-01-19 23:49 | admin |  | 10800 | 28800 | Medium | admin | Selected for Development | 18000 | 12 | 2
84 | C | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-3 | 10313 | 2019-01-19 19:44 | 2019-01-19 23:49 | admin |  | 10800 | 28800 | Medium | admin | Selected for Development | 18000 | 12 | 2 |  |  | 10243 | quintusQ | quintusq | 2019-01-19 23:40 | 2019-01-19 23:40 | quintusQ | [7 empty] | With the new character logging system, this is easy. I'll have it ready for you to look at this afternoon.
85 | C | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-3 | 10313 | 2019-01-19 19:44 | 2019-01-19 23:49 | admin |  | 10800 | 28800 | Medium | admin | Selected for Development | 18000 | 12 | 2 |  |  | 10248 | quintusQ | quintusq | 2019-01-19 23:49 | 2019-01-19 23:49 | quintusQ | [7 empty] | It's ready. It's running in DEV and I threw up a dashboard on MON001 to show it happening in realtime.
86 | W | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-3 | 10313 | 2019-01-19 19:44 | 2019-01-19 23:49 | admin |  | 10800 | 28800 | Medium | admin | Selected for Development | 18000 | 12 | 2 | [8 empty] | 10269 | Quintus Quarrel | quintusq | 2019-01-19 23:46 | 2019-01-28 15:00 | 2019-01-19 23:46 | 18000 |  | Added character powerup usage logging and committed to DEV.
87 | I | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-2 | 10312 | 2019-01-19 19:43 | 2019-01-19 23:28 | admin |  | 0 | 57600 | Medium | admin | In Progress | 68400 | 16 | 2
88 | C | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-2 | 10312 | 2019-01-19 19:43 | 2019-01-19 23:28 | admin |  | 0 | 57600 | Medium | admin | In Progress | 68400 | 16 | 2 |  |  | 10233 | pennyP | pennyp | 2019-01-19 23:09 | 2019-01-19 23:09 | pennyP | [7 empty] | We're not changing the value of a setting. We're adding a brand new behavioural limit. That said, it shouldn't take more than a couple of days.
89 | C | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-2 | 10312 | 2019-01-19 19:43 | 2019-01-19 23:28 | admin |  | 0 | 57600 | Medium | admin | In Progress | 68400 | 16 | 2 |  |  | 10238 | pennyP | pennyp | 2019-01-19 23:28 | 2019-01-19 23:28 | pennyP | [7 empty] | All done. It's ready for test.
90 | W | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-2 | 10312 | 2019-01-19 19:43 | 2019-01-19 23:28 | admin |  | 0 | 57600 | Medium | admin | In Progress | 68400 | 16 | 2 | [8 empty] | 10252 | Penny Price | pennyp | 2019-01-19 23:17 | 2019-01-21 17:00 | 2019-01-19 23:17 | 10800 |  | Adding new behavioural limit.
91 | W | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-2 | 10312 | 2019-01-19 19:43 | 2019-01-19 23:28 | admin |  | 0 | 57600 | Medium | admin | In Progress | 68400 | 16 | 2 | [8 empty] | 10255 | Penny Price | pennyp | 2019-01-19 23:25 | 2019-01-22 17:00 | 2019-01-19 23:25 | 28800 |  | Unit testing
92 | W | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-2 | 10312 | 2019-01-19 19:43 | 2019-01-19 23:28 | admin |  | 0 | 57600 | Medium | admin | In Progress | 68400 | 16 | 2 | [8 empty] | 10258 | Penny Price | pennyp | 2019-01-19 23:28 | 2019-01-23 17:00 | 2019-01-19 23:28 | 28800 |  | All done. It's ready for test.
93 | I | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-1 | 10311 | 2019-01-19 19:43 | 2019-01-19 23:42 | admin |  | 75600 | 172800 | Medium | admin | Done | 97200 | 22 | 2
94 | C | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-1 | 10311 | 2019-01-19 19:43 | 2019-01-19 23:42 | admin |  | 75600 | 172800 | Medium | admin | Done | 97200 | 22 | 2 |  |  | 10204 | oscarO | oscaro | 2019-01-19 21:23 | 2019-01-19 21:23 | oscarO | [7 empty] | I added the shield object this morning and attached it to the enemy object.
95 | C | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-1 | 10311 | 2019-01-19 19:43 | 2019-01-19 23:42 | admin |  | 75600 | 172800 | Medium | admin | Done | 97200 | 22 | 2 |  |  | 10217 | oscarO | oscaro | 2019-01-19 22:15 | 2019-01-19 22:15 | oscarO | [7 empty] | I added collision-detection for hero shots and decreasing shield strength with hits.
96 | C | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-1 | 10311 | 2019-01-19 19:43 | 2019-01-19 23:42 | admin |  | 75600 | 172800 | Medium | admin | Done | 97200 | 22 | 2 |  |  | 10226 | oscarO | oscaro | 2019-01-19 22:37 | 2019-01-19 22:37 | oscarO | [7 empty] | I added the shield collapse and checked it into dev. It's ready for testing.
97 | W | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-1 | 10311 | 2019-01-19 19:43 | 2019-01-19 23:42 | admin |  | 75600 | 172800 | Medium | admin | Done | 97200 | 22 | 2 | [8 empty] | 10205 | Oscar Otto | oscaro | 2019-01-19 21:22 | 2019-01-04 11:00 | 2019-01-19 21:22 | 10800 |  | Added new shield and shields objects
98 | W | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-1 | 10311 | 2019-01-19 19:43 | 2019-01-19 23:42 | admin |  | 75600 | 172800 | Medium | admin | Done | 97200 | 22 | 2 | [8 empty] | 10218 | Oscar Otto | oscaro | 2019-01-19 22:12 | 2019-01-07 17:00 | 2019-01-19 22:12 | 28800 |  | Adding collission detection for shield and hero shot.
99 | W | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-1 | 10311 | 2019-01-19 19:43 | 2019-01-19 23:42 | admin |  | 75600 | 172800 | Medium | admin | Done | 97200 | 22 | 2 | [8 empty] | 10220 | Oscar Otto | oscaro | 2019-01-19 22:16 | 2019-01-08 17:00 | 2019-01-19 22:16 | 28800 |  | Finished health impact updates for enemy shields being hit.
100 | W | GAMEDEV | 10206 | Game Dev | pennyP | GAMEDEV-1 | 10311 | 2019-01-19 19:43 | 2019-01-19 23:42 | admin |  | 75600 | 172800 | Medium | admin | Done | 97200 | 22 | 2 | [8 empty] | 10224 | Oscar Otto | oscaro | 2019-01-19 22:22 | 2019-01-09 17:00 | 2019-01-19 22:22 | 28800 |  | Tidied up the code and committed it to DEV.
101 | I | IT | 10207 | Information Technology | saraS | IT-5 | 10200 | 2018-12-11 22:25 | 2019-01-19 23:51 | admin |  | 0 |  | Medium | admin | Done | 61200 | 14 | 3
102 | C | IT | 10207 | Information Technology | saraS | IT-5 | 10200 | 2018-12-11 22:25 | 2019-01-19 23:51 | admin |  | 0 |  | Medium | admin | Done | 61200 | 14 | 3 |  |  | 10241 | tiffanyT | tiffanyt | 2019-01-19 23:33 | 2019-01-19 23:34 | tiffanyT | [7 empty] | The new developer machine image passed smoke testing. Oscar, would you please try using it as your dev machine for a few days?
103 | C | IT | 10207 | Information Technology | saraS | IT-5 | 10200 | 2018-12-11 22:25 | 2019-01-19 23:51 | admin |  | 0 |  | Medium | admin | Done | 61200 | 14 | 3 |  |  | 10246 | oscarO | oscaro | 2019-01-19 23:47 | 2019-01-19 23:47 | oscarO | [7 empty] | I'm using it today and haven't seen any problems yet. I'll let you know tomorrow morning once it's been through a full cycle.
104 | C | IT | 10207 | Information Technology | saraS | IT-5 | 10200 | 2018-12-11 22:25 | 2019-01-19 23:51 | admin |  | 0 |  | Medium | admin | Done | 61200 | 14 | 3 |  |  | 10249 | oscarO | oscaro | 2019-01-19 23:51 | 2019-01-19 23:51 | oscarO | [7 empty] | Everything went well. I'll start having the other team members switch over to this image one-at-a-time. Thanks!
105 | W | IT | 10207 | Information Technology | saraS | IT-5 | 10200 | 2018-12-11 22:25 | 2019-01-19 23:51 | admin |  | 0 |  | Medium | admin | Done | 61200 | 14 | 3 | [8 empty] | 10259 | Tiffany Tango | tiffanyt | 2019-01-19 23:29 | 2019-01-23 17:00 | 2019-01-19 23:29 | 28800 |  | Installing new software with all updates.
106 | W | IT | 10207 | Information Technology | saraS | IT-5 | 10200 | 2018-12-11 22:25 | 2019-01-19 23:51 | admin |  | 0 |  | Medium | admin | Done | 61200 | 14 | 3 | [8 empty] | 10261 | Tiffany Tango | tiffanyt | 2019-01-19 23:33 | 2019-01-24 15:00 | 2019-01-19 23:33 | 21600 |  | Testing individual software and test builds.
107 | W | IT | 10207 | Information Technology | saraS | IT-5 | 10200 | 2018-12-11 22:25 | 2019-01-19 23:51 | admin |  | 0 |  | Medium | admin | Done | 61200 | 14 | 3 | [8 empty] | 10267 | Oscar Otto | oscaro | 2019-01-19 23:43 | 2019-01-28 11:00 | 2019-01-19 23:43 | 7200 |  | Configuring the new developer machine with my settings. I scripted them out to save this time in the future and I'll write them up in Confluence to share with the rest of the team.
108 | W | IT | 10207 | Information Technology | saraS | IT-5 | 10200 | 2018-12-11 22:25 | 2019-01-19 23:51 | admin |  | 0 |  | Medium | admin | Done | 61200 | 14 | 3 | [8 empty] | 10270 | Oscar Otto | oscaro | 2019-01-19 23:51 | 2019-01-29 10:00 | 2019-01-19 23:51 | 3600 |  | Documenting test case results.
109 | I | IT | 10207 | Information Technology | saraS | IT-4 | 10317 | 2019-01-19 19:45 | 2019-01-19 23:05 | admin |  | 18000 | 43200 | Medium | admin | To Do | 25200 | 18 | 2
110 | C | IT | 10207 | Information Technology | saraS | IT-4 | 10317 | 2019-01-19 19:45 | 2019-01-19 23:05 | admin |  | 18000 | 43200 | Medium | admin | To Do | 25200 | 2 | 2 |  |  | 10228 | uffaU | uffau | 2019-01-19 22:48 | 2019-01-19 22:48 | uffaU | [7 empty] | I've created the new health checks
111 | W | IT | 10207 | Information Technology | saraS | IT-4 | 10317 | 2019-01-19 19:45 | 2019-01-19 23:05 | admin |  | 18000 | 43200 | Medium | admin | To Do | 25200 | 2 | 2 | [8 empty] | 10235 | Uffa Urlot | uffau | 2019-01-19 22:45 | 2019-01-16 16:00 | 2019-01-19 22:45 | 14400 |  | Creating health scripts.
112 | W | IT | 10207 | Information Technology | saraS | IT-4 | 10317 | 2019-01-19 19:45 | 2019-01-19 23:05 | admin |  | 18000 | 43200 | Medium | admin | To Do | 25200 | 2 | 2 | [8 empty] | 10245 | Uffa Urlot | uffau | 2019-01-19 23:05 | 2019-01-20 12:00 | 2019-01-19 23:05 | 10800 |  | The new alias records are in place.
113 | I | IT | 10207 | Information Technology | saraS | IT-3 | 10316 | 2019-01-19 19:45 | 2019-01-19 23:32 | admin |  | 86400 | 86400 | Medium | admin | Selected for Development | 0 | 3 | 2
114 | I | IT | 10207 | Information Technology | saraS | IT-2 | 10315 | 2019-01-19 19:44 | 2019-01-19 22:26 | admin |  | 36000 | 86400 | Medium | admin | In Progress | 50400 | 6 | 2
115 | C | IT | 10207 | Information Technology | saraS | IT-2 | 10315 | 2019-01-19 19:44 | 2019-01-19 22:26 | admin |  | 36000 | 86400 | Medium | admin | In Progress | 50400 | 6 | 2 |  |  | 10215 | saraS | saras | 2019-01-19 21:45 | 2019-01-19 21:45 | saraS | [7 empty] | The new image passed testing.
116 | C | IT | 10207 | Information Technology | saraS | IT-2 | 10315 | 2019-01-19 19:44 | 2019-01-19 22:26 | admin |  | 36000 | 86400 | Medium | admin | In Progress | 50400 | 6 | 2 |  |  | 10219 | saraS | saras | 2019-01-19 22:18 | 2019-01-19 22:18 | saraS | [7 empty] | Production boxes have been created with the new image. They are applying restores now.
117 | C | IT | 10207 | Information Technology | saraS | IT-2 | 10315 | 2019-01-19 19:44 | 2019-01-19 22:26 | admin |  | 36000 | 86400 | Medium | admin | In Progress | 50400 | 6 | 2 |  |  | 10220 | saraS | saras | 2019-01-19 22:26 | 2019-01-19 22:26 | saraS | [7 empty] | All transaction log backups have been applied and these boxes ave been added to the cluster.
118 | W | IT | 10207 | Information Technology | saraS | IT-2 | 10315 | 2019-01-19 19:44 | 2019-01-19 22:26 | admin |  | 36000 | 86400 | Medium | admin | In Progress | 50400 | 6 | 2 | [8 empty] | 10216 | Sara Smith | saras | 2019-01-19 21:45 | 2019-01-07 15:00 | 2019-01-19 21:45 | 21600 |  | Testing new image
119 | W | IT | 10207 | Information Technology | saraS | IT-2 | 10315 | 2019-01-19 19:44 | 2019-01-19 22:26 | admin |  | 36000 | 86400 | Medium | admin | In Progress | 50400 | 6 | 2 | [8 empty] | 10221 | Sara Smith | saras | 2019-01-19 22:17 | 2019-01-09 15:00 | 2019-01-19 22:17 | 21600 |  | Production rollout and monitoring.
120 | W | IT | 10207 | Information Technology | saraS | IT-2 | 10315 | 2019-01-19 19:44 | 2019-01-19 22:26 | admin |  | 36000 | 86400 | Medium | admin | In Progress | 50400 | 6 | 2 | [8 empty] | 10225 | Sara Smith | saras | 2019-01-19 22:25 | 2019-01-10 10:00 | 2019-01-19 22:25 | 7200 |  | Changing cluster configuration
121 | I | IT | 10207 | Information Technology | saraS | IT-1 | 10314 | 2019-01-19 19:44 | 2019-01-19 20:39 | admin |  | 39600 | 57600 | Medium | admin | Done | 18000 | 11 | 2
122 | C | IT | 10207 | Information Technology | saraS | IT-1 | 10314 | 2019-01-19 19:44 | 2019-01-19 20:39 | admin |  | 39600 | 57600 | Medium | admin | Done | 18000 | 11 | 2 |  |  | 10200 | robertR | robertr | 2019-01-19 20:37 | 2019-01-19 20:37 | robertR | [7 empty] | I see 14 package(s) needed for security, out of 16 available
123 | C | IT | 10207 | Information Technology | saraS | IT-1 | 10314 | 2019-01-19 19:44 | 2019-01-19 20:39 | admin |  | 39600 | 57600 | Medium | admin | Done | 18000 | 11 | 2 |  |  | 10201 | robertR | robertr | 2019-01-19 20:39 | 2019-01-19 20:39 | robertR | [7 empty] | The updates are done and the smoke tests are running.
124 | W | IT | 10207 | Information Technology | saraS | IT-1 | 10314 | 2019-01-19 19:44 | 2019-01-19 20:39 | admin |  | 39600 | 57600 | Medium | admin | Done | 18000 | 11 | 2 | [8 empty] | 10200 | Robert Romeo | robertr | 2019-01-19 20:38 | 2019-01-02 12:00 | 2019-01-19 20:38 | 10800 |  | Reviewing updates.
125 | W | IT | 10207 | Information Technology | saraS | IT-1 | 10314 | 2019-01-19 19:44 | 2019-01-19 20:39 | admin |  | 39600 | 57600 | Medium | admin | Done | 18000 | 11 | 2 | [8 empty] | 10201 | Robert Romeo | robertr | 2019-01-19 20:39 | 2019-01-02 14:00 | 2019-01-19 20:39 | 7200 |  | Applying updates and monitoring.
126 | I | PM | 10208 | Project Management | victorV | PM-1 | 10318 | 2019-01-19 19:46 | 2019-01-19 21:42 | admin |  | 0 | 86400 | Medium | admin | Done | 97200 | 6 | 3
127 | C | PM | 10208 | Project Management | victorV | PM-1 | 10318 | 2019-01-19 19:46 | 2019-01-19 21:42 | admin |  | 0 | 86400 | Medium | admin | Done | 97200 | 6 | 3 |  |  | 10209 | victorV | victorv | 2019-01-19 21:35 | 2019-01-19 21:35 | victorV | [7 empty] | David D., could you give these a read over and make sure it meets your architecture needs?
128 | C | PM | 10208 | Project Management | victorV | PM-1 | 10318 | 2019-01-19 19:46 | 2019-01-19 21:42 | admin |  | 0 | 86400 | Medium | admin | Done | 97200 | 6 | 3 |  |  | 10213 | davidD | davidd | 2019-01-19 21:42 | 2019-01-19 21:42 | davidD | [7 empty] | It's everything I need and more! Thanks!
129 | W | PM | 10208 | Project Management | victorV | PM-1 | 10318 | 2019-01-19 19:46 | 2019-01-19 21:42 | admin |  | 0 | 86400 | Medium | admin | Done | 97200 | 6 | 3 | [8 empty] | 10202 | Victor Vineman | victorv | 2019-01-19 20:48 | 2019-01-02 17:00 | 2019-01-19 20:48 | 28800 |  | Reviewing requirements and creating draft.
130 | W | PM | 10208 | Project Management | victorV | PM-1 | 10318 | 2019-01-19 19:46 | 2019-01-19 21:42 | admin |  | 0 | 86400 | Medium | admin | Done | 97200 | 6 | 3 | [8 empty] | 10204 | Victor Vineman | victorv | 2019-01-19 21:21 | 2019-01-03 17:00 | 2019-01-19 21:21 | 28800 |  | Filling out details in the draft.
131 | W | PM | 10208 | Project Management | victorV | PM-1 | 10318 | 2019-01-19 19:46 | 2019-01-19 21:42 | admin |  | 0 | 86400 | Medium | admin | Done | 97200 | 6 | 3 | [8 empty] | 10210 | Victor Vineman | victorv | 2019-01-19 21:34 | 2019-01-04 17:00 | 2019-01-19 21:34 | 28800 |  | Finishing up the document.
132 | W | PM | 10208 | Project Management | victorV | PM-1 | 10318 | 2019-01-19 19:46 | 2019-01-19 21:42 | admin |  | 0 | 86400 | Medium | admin | Done | 97200 | 6 | 3 | [8 empty] | 10214 | David Doswell | davidd | 2019-01-19 21:42 | 2019-01-07 12:00 | 2019-01-19 21:42 | 10800 |  | Reviewing the new document.
133 | I | SUP | 10100 | Support | admin | SUP-1 | 10100 | 2018-12-10 19:37 | 2018-12-10 20:49 | admin |  | 0 |  | Medium | admin | Done | 900 | 20 | 1
134 | W | SUP | 10100 | Support | admin | SUP-1 | 10100 | 2018-12-10 19:37 | 2018-12-10 20:49 | admin |  | 0 |  | Medium | admin | Done | 900 | 20 | 1 | [8 empty] | 10100 | Alex Alexander | alexa | 2018-12-10 20:49 | 2018-12-10 20:49 | 2018-12-10 20:49 | 900 |  | I did something.
135 | I | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-3 | 10321 | 2019-01-19 19:49 | 2019-01-19 23:10 | admin |  | 0 | 43200 | Medium | admin | Selected for Development | 57600 | 13 | 2
136 | C | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-3 | 10321 | 2019-01-19 19:49 | 2019-01-19 23:10 | admin |  | 0 | 43200 | Medium | admin | Selected for Development | 57600 | 13 | 2 |  |  | 10229 | zoeZ | zoez | 2019-01-19 22:54 | 2019-01-19 22:54 | zoeZ | [7 empty] | I've put up the basic page in DEV
137 | C | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-3 | 10321 | 2019-01-19 19:49 | 2019-01-19 23:10 | admin |  | 0 | 43200 | Medium | admin | Selected for Development | 57600 | 13 | 2 |  |  | 10234 | zoeZ | zoez | 2019-01-19 23:10 | 2019-01-19 23:10 | zoeZ | [7 empty] | I've added the forward/back links for videos that are in a series and I'll create a ticket to update them once the series are complete.
138 | W | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-3 | 10321 | 2019-01-19 19:49 | 2019-01-19 23:10 | admin |  | 0 | 43200 | Medium | admin | Selected for Development | 57600 | 13 | 2 | [8 empty] | 10238 | Zoe Zebra | zoez | 2019-01-19 22:53 | 2019-01-16 17:00 | 2019-01-19 22:53 | 28800 |  | Developing page template
139 | W | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-3 | 10321 | 2019-01-19 19:49 | 2019-01-19 23:10 | admin |  | 0 | 43200 | Medium | admin | Selected for Development | 57600 | 13 | 2 | [8 empty] | 10239 | Zoe Zebra | zoez | 2019-01-19 22:53 | 2019-01-17 15:00 | 2019-01-19 22:53 | 14400 |  | Adjustments based on peer review.
140 | W | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-3 | 10321 | 2019-01-19 19:49 | 2019-01-19 23:10 | admin |  | 0 | 43200 | Medium | admin | Selected for Development | 57600 | 13 | 2 | [8 empty] | 10247 | Zoe Zebra | zoez | 2019-01-19 23:10 | 2019-01-21 14:00 | 2019-01-19 23:10 | 14400 |  | Added new navigation feature.
141 | I | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-2 | 10320 | 2019-01-19 19:48 | 2019-01-19 23:48 | admin |  | 39600 | 86400 | Medium | admin | In Progress | 46800 | 16 | 3
142 | C | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-2 | 10320 | 2019-01-19 19:48 | 2019-01-19 23:48 | admin |  | 39600 | 86400 | Medium | admin | In Progress | 46800 | 16 | 3 |  |  | 10245 | yanniY | yanniy | 2019-01-19 23:45 | 2019-01-19 23:45 | yanniY | [7 empty] | Penny, can you send me the location of the 3D models for characters?
143 | C | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-2 | 10320 | 2019-01-19 19:48 | 2019-01-19 23:48 | admin |  | 39600 | 86400 | Medium | admin | In Progress | 46800 | 16 | 3 |  |  | 10247 | pennyP | pennyp | 2019-01-19 23:48 | 2019-01-19 23:48 | pennyP | [7 empty] | No problem, Yanni. They're at ProductY > assets > models > heros. And... thanks for building this gallery!
144 | W | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-2 | 10320 | 2019-01-19 19:48 | 2019-01-19 23:48 | admin |  | 39600 | 86400 | Medium | admin | In Progress | 46800 | 16 | 3 | [8 empty] | 10264 | Yanni Yodel | yanniy | 2019-01-19 23:38 | 2019-01-25 17:00 | 2019-01-19 23:38 | 28800 |  | Developing mock-up.
145 | W | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-2 | 10320 | 2019-01-19 19:48 | 2019-01-19 23:48 | admin |  | 39600 | 86400 | Medium | admin | In Progress | 46800 | 16 | 3 | [8 empty] | 10268 | Yanni Yodel | yanniy | 2019-01-19 23:44 | 2019-01-28 14:00 | 2019-01-19 23:44 | 18000 |  | Adjusting styles
146 | I | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-1 | 10319 | 2019-01-19 19:48 | 2019-01-19 23:00 | admin |  | 104400 | 144000 | Medium | admin | Done | 39600 | 26 | 3
147 | C | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-1 | 10319 | 2019-01-19 19:48 | 2019-01-19 23:00 | admin |  | 104400 | 144000 | Medium | admin | Done | 39600 | 26 | 3 |  |  | 10205 | walterW | walterw | 2019-01-19 21:24 | 2019-01-19 21:24 | walterW | [7 empty] | i recommend using a third-party provider for this. They can do it cheaper and more completely.
148 | C | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-1 | 10319 | 2019-01-19 19:48 | 2019-01-19 23:00 | admin |  | 104400 | 144000 | Medium | admin | Done | 39600 | 26 | 3 |  |  | 10212 | zoeZ | zoez | 2019-01-19 21:41 | 2019-01-19 21:41 | zoeZ | [7 empty] | I'll second that opinion. We did it in an afternoon at my last company using a third-part tool.
149 | C | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-1 | 10319 | 2019-01-19 19:48 | 2019-01-19 23:00 | admin |  | 104400 | 144000 | Medium | admin | Done | 39600 | 26 | 3 |  |  | 10230 | walterW | walterw | 2019-01-19 22:59 | 2019-01-19 22:59 | walterW | [7 empty] | I've done it. Check it out in dev. You'll see the privacy and cookie notices. Plus, there is a cookies management feature.
150 | W | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-1 | 10319 | 2019-01-19 19:48 | 2019-01-19 23:00 | admin |  | 104400 | 144000 | Medium | admin | Done | 39600 | 26 | 3 | [8 empty] | 10206 | Walter Walkman | walterw | 2019-01-19 21:25 | 2019-01-04 13:00 | 2019-01-19 21:25 | 7200 |  | Reviewing options for this feature.
151 | W | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-1 | 10319 | 2019-01-19 19:48 | 2019-01-19 23:00 | admin |  | 104400 | 144000 | Medium | admin | Done | 39600 | 26 | 3 | [8 empty] | 10213 | Zoe Zebra | zoez | 2019-01-19 21:40 | 2019-01-07 11:00 | 2019-01-19 21:40 | 3600 |  | Reviewing suggestion
152 | W | WEBDEV | 10209 | Web Dev | zoeZ | WEBDEV-1 | 10319 | 2019-01-19 19:48 | 2019-01-19 23:00 | admin |  | 104400 | 144000 | Medium | admin | Done | 39600 | 26 | 3 | [8 empty] | 10243 | Walter Walkman | walterw | 2019-01-19 22:59 | 2019-01-18 17:00 | 2019-01-19 23:00 | 28800 |  | Implementing privacy policy and cookies requirements.

## EmployeeWork
recordType | W
projectName | (Multiple Items)
Row Labels | Sum of worklogTimeSpent
admin | 900
Alex Alexander | 82800
Brian Boswell | 111600
Candice Chapman | 7200
David Doswell | 183600
Eric Ericson | 21600
Frank Frampton | 82800
Gabby Golf | 97200
Grand Total | 587700

## ProjectWork
recordType | W
Row Labels | Sum of worklogTimeSpent
AppDev | 158400
Architecture | 248400
Art | 180000
Development | 900
Grand Total | 587700

## NewFeatureInterest
recordType | I
projectName | (Multiple Items)
issueStatus | To Do
Row Labels | Sum of issueVotes
DEV-4 | 22
ART-3 | 14
Grand Total | 36

## ProjectPipeline
recordType | I
projectName | (Multiple Items)
Row Labels | Count of issueKey
Done | 5
In Progress | 5
Selected for Development | 1
To Do | 2
Grand Total | 13

## Dashboard
Project Dashboard
Work Logged By Employee
Project Work Loads
New Feature Interest
Project Pipeline
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.